## QA register
Test ID | Area | Feature | Test | Expected Result | Actual Result | Device/Browser | Pass/Fail | Severity | Evidence | Bug ID | Retest Result
REG-001 | Payments & wallet | Tests | Basket multiple comps one payment | Basket multiple comps one payment — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_basket_multiple_comps_one_payment (0.458 s)
REG-002 | Payments & wallet | Tests | Cancelled checkout releases tickets and credit | Cancelled checkout releases tickets and credit — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_cancelled_checkout_releases_tickets_and_credit (0.350 s)
REG-003 | Security & access | Tests | Csrf and 404 | Csrf and 404 — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_csrf_and_404 (0.468 s)
REG-004 | Security & access | Tests | First signup is not admin | First signup is not admin — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_first_signup_is_not_admin (0.633 s)
REG-005 | Competitions, draws & instant wins | Tests | Instant commitment verifiable and locked | Instant commitment verifiable and locked — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_instant_commitment_verifiable_and_locked (0.430 s)
REG-006 | Payments & wallet | Tests | Instant win credit and wallet spend | Instant win credit and wallet spend — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_instant_win_credit_and_wallet_spend (0.457 s)
REG-007 | General | Tests | Lucky dip and per user cap | Lucky dip and per user cap — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_lucky_dip_and_per_user_cap (0.479 s)
REG-008 | General | Tests | Multibuy discount | Multibuy discount — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_multibuy_discount (0.390 s)
REG-009 | Security & access | Tests | No automatic admin and cli | No automatic admin and cli — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_no_automatic_admin_and_cli (0.515 s)
REG-010 | Ticket allocation & basket | Tests | No oversell under concurrency | No oversell under concurrency — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_no_oversell_under_concurrency (1.375 s)
REG-011 | General | Tests | Old announcement setting migrates | Old announcement setting migrates — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_old_announcement_setting_migrates (0.391 s)
REG-012 | General | Tests | Pages render | Pages render — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_pages_render (1.037 s)
REG-013 | General | Tests | Password reset | Password reset — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_password_reset (0.615 s)
REG-014 | General | Tests | Pick numbers and clash | Pick numbers and clash — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_pick_numbers_and_clash (0.695 s)
REG-015 | Competitions, draws & instant wins | Tests | Postal entry and verifiable draw | Postal entry and verifiable draw — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_postal_entry_and_verifiable_draw (0.408 s)
REG-016 | Promotions, points & referrals | Tests | Promo code | Promo code — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Tests::test_promo_code (0.405 s)
REG-017 | Promotions, points & referrals | Tests | Referral bonus once | Referral bonus once — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Tests::test_referral_bonus_once (0.492 s)
REG-018 | Responsible play | Tests | Self exclusion | Self exclusion — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Tests::test_self_exclusion (0.347 s)
REG-019 | General | Tests | Settings live banner | Settings live banner — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_settings_live_banner (0.400 s)
REG-020 | Responsible play | Tests | Spend limits | Spend limits — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Tests::test_spend_limits (0.502 s)
REG-021 | General | Tests | Stale holds expire | Stale holds expire — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_stale_holds_expire (0.486 s)
REG-022 | Payments & wallet | Tests | Stripe webhook signature and idempotency | Stripe webhook signature and idempotency — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_stripe_webhook_signature_and_idempotency (0.404 s)
REG-023 | General | Tests | Under 18 rejected | Under 18 rejected — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_under_18_rejected (0.348 s)
REG-024 | Payments & wallet | Tests | Withdrawal flow | Withdrawal flow — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Tests::test_withdrawal_flow (0.652 s)
REG-025 | General | Tests | Wrong answer not added | Wrong answer not added — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Tests::test_wrong_answer_not_added (0.347 s)
REG-026 | Competitions, draws & instant wins | GameTests | Buy play reveal credits once | Buy play reveal credits once — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::GameTests::test_buy_play_reveal_credits_once (0.545 s)
REG-027 | Competitions, draws & instant wins | GameTests | Game has no draw and hides spoilers | Game has no draw and hides spoilers — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::GameTests::test_game_has_no_draw_and_hides_spoilers (0.507 s)
REG-028 | Competitions, draws & instant wins | GameTests | Only selected prices and drafts | Only selected prices and drafts — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::GameTests::test_only_selected_prices_and_drafts (0.343 s)
REG-029 | Competitions, draws & instant wins | GameTests | Random games live and sane | Random games live and sane — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::GameTests::test_random_games_live_and_sane (0.428 s)
REG-030 | Competitions, draws & instant wins | GameTests | Starter games | Starter games — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::GameTests::test_starter_games (0.570 s)
REG-031 | Competitions, draws & instant wins | GameTests | Unrevealed wins paid automatically | Unrevealed wins paid automatically — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::GameTests::test_unrevealed_wins_paid_automatically (0.449 s)
REG-032 | Competitions, draws & instant wins | V4Tests | Auto draw runs and manual opt out | Auto draw runs and manual opt out — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::V4Tests::test_auto_draw_runs_and_manual_opt_out (0.436 s)
REG-033 | Payments & wallet | V4Tests | Cancel refunds cash once | Cancel refunds cash once — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::V4Tests::test_cancel_refunds_cash_once (0.367 s)
REG-034 | General | V4Tests | Cash prize goes to cash and is spent after credit | Cash prize goes to cash and is spent after credit — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::V4Tests::test_cash_prize_goes_to_cash_and_is_spent_after_credit (0.411 s)
REG-035 | General | V4Tests | Email verification link | Email verification link — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::V4Tests::test_email_verification_link (0.461 s)
REG-036 | General | V4Tests | Free daily once per day and needs verified email | Free daily once per day and needs verified email — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::V4Tests::test_free_daily_once_per_day_and_needs_verified_email (0.538 s)
REG-037 | General | V4Tests | Image upload checked and converted | Image upload checked and converted — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::V4Tests::test_image_upload_checked_and_converted (0.665 s)
REG-038 | General | V4Tests | Login lockout | Login lockout — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::V4Tests::test_login_lockout (1.268 s)
REG-039 | Promotions, points & referrals | V4Tests | Points awarded and redeemed | Points awarded and redeemed — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::V4Tests::test_points_awarded_and_redeemed (0.383 s)
REG-040 | Promotions, points & referrals | V4Tests | Seo search share stats and referral param | Seo search share stats and referral param — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::V4Tests::test_seo_search_share_stats_and_referral_param (0.593 s)
REG-041 | Payments & wallet | CreditCardTests | Credit card refunded tickets released balance returned | Credit card refunded tickets released balance returned — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::CreditCardTests::test_credit_card_refunded_tickets_released_balance_returned (0.375 s) | BUG-007 | Pass after fix
REG-042 | General | CreditCardTests | Debit card accepted | Debit card accepted — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CreditCardTests::test_debit_card_accepted (0.361 s)
REG-043 | Payments & wallet | CreditCardTests | Failed refund flagged for admin | Failed refund flagged for admin — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::CreditCardTests::test_failed_refund_flagged_for_admin (0.389 s)
REG-044 | Payments & wallet | CreditCardTests | Non card payment accepted | Non card payment accepted — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::CreditCardTests::test_non_card_payment_accepted (0.349 s)
REG-045 | Ticket allocation & basket | OverhaulTests | Basket quantity promo preview and totals | Basket quantity promo preview and totals — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::OverhaulTests::test_basket_quantity_promo_preview_and_totals (0.461 s)
REG-046 | Payments & wallet | OverhaulTests | Cancelled payment restores basket | Cancelled payment restores basket — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::OverhaulTests::test_cancelled_payment_restores_basket (0.437 s)
REG-047 | Responsible play | OverhaulTests | Contact form validates and rate limits | Contact form validates and rate limits — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OverhaulTests::test_contact_form_validates_and_rate_limits (0.386 s)
REG-048 | Customer & admin experience | OverhaulTests | Error pages have a way out | Error pages have a way out — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OverhaulTests::test_error_pages_have_a_way_out (0.351 s)
REG-049 | Customer & admin experience | OverhaulTests | Missing answer gives clear error | Missing answer gives clear error — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OverhaulTests::test_missing_answer_gives_clear_error (0.410 s)
REG-050 | Customer & admin experience | OverhaulTests | No placeholders or draft banners for visitors | No placeholders or draft banners for visitors — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OverhaulTests::test_no_placeholders_or_draft_banners_for_visitors (0.430 s)
REG-051 | Customer & admin experience | OverhaulTests | Old urls redirect permanently | Old urls redirect permanently — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OverhaulTests::test_old_urls_redirect_permanently (0.366 s)
REG-052 | Security & access | OverhaulTests | Order detail and isolation | Order detail and isolation — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::OverhaulTests::test_order_detail_and_isolation (0.648 s)
REG-053 | Customer & admin experience | OverhaulTests | Sitemap keeps recent results and drops cancelled | Sitemap keeps recent results and drops cancelled — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OverhaulTests::test_sitemap_keeps_recent_results_and_drops_cancelled (0.447 s) | BUG-002 | Pass after fix
REG-054 | Customer & admin experience | OverhaulTests | Unique titles canonical and noindex | Unique titles canonical and noindex — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OverhaulTests::test_unique_titles_canonical_and_noindex (0.666 s)
REG-055 | General | DeleteTests | Bulk delete and start fresh | Bulk delete and start fresh — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::DeleteTests::test_bulk_delete_and_start_fresh (0.705 s)
REG-056 | Payments & wallet | DeleteTests | Delete unsold and refuse unrefunded | Delete unsold and refuse unrefunded — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::DeleteTests::test_delete_unsold_and_refuse_unrefunded (0.729 s)
REG-057 | Competitions, draws & instant wins | CreateTests | Bad prize line and game needs prizes | Bad prize line and game needs prizes — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::CreateTests::test_bad_prize_line_and_game_needs_prizes (0.456 s)
REG-058 | General | CreateTests | Free daily from form | Free daily from form — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CreateTests::test_free_daily_from_form (0.346 s)
REG-059 | Competitions, draws & instant wins | CreateTests | Game with prize table in one go | Game with prize table in one go — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::CreateTests::test_game_with_prize_table_in_one_go (0.428 s)
REG-060 | General | CreateTests | Schedule and unpublish | Schedule and unpublish — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CreateTests::test_schedule_and_unpublish (0.439 s)
REG-061 | General | CreateTests | Unpublish refused once entered | Unpublish refused once entered — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CreateTests::test_unpublish_refused_once_entered (0.507 s)
REG-062 | Payments & wallet | DepositTests | Bad amounts unverified and break | Bad amounts unverified and break — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::DepositTests::test_bad_amounts_unverified_and_break (0.478 s)
REG-063 | Payments & wallet | DepositTests | Cancelled checkout returns deposit | Cancelled checkout returns deposit — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::DepositTests::test_cancelled_checkout_returns_deposit (0.380 s)
REG-064 | Payments & wallet | DepositTests | Deposit spend and limits counted once | Deposit spend and limits counted once — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::DepositTests::test_deposit_spend_and_limits_counted_once (0.518 s)
REG-065 | Payments & wallet | DepositTests | Refund unspent and not withdrawable | Refund unspent and not withdrawable — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::DepositTests::test_refund_unspent_and_not_withdrawable (0.514 s)
REG-066 | Payments & wallet | DepositTests | Stripe webhook deposit and credit card | Stripe webhook deposit and credit card — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::DepositTests::test_stripe_webhook_deposit_and_credit_card (0.431 s)
REG-067 | Ticket allocation & basket | IntegrityTests | Basket kept through sign up | Basket kept through sign up — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_basket_kept_through_sign_up (0.589 s)
REG-068 | Payments & wallet | IntegrityTests | Break blocks free play and deposits | Break blocks free play and deposits — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_break_blocks_free_play_and_deposits (0.471 s)
REG-069 | Payments & wallet | IntegrityTests | Break releases checkouts in progress | Break releases checkouts in progress — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_break_releases_checkouts_in_progress (0.510 s)
REG-070 | Payments & wallet | IntegrityTests | Cancellation refunds each part as it was paid | Cancellation refunds each part as it was paid — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_cancellation_refunds_each_part_as_it_was_paid (0.499 s)
REG-071 | Payments & wallet | IntegrityTests | Double click creates one checkout | Double click creates one checkout — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_double_click_creates_one_checkout (0.493 s)
REG-072 | Competitions, draws & instant wins | IntegrityTests | Draw snapshot is permanent | Draw snapshot is permanent — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_draw_snapshot_is_permanent (0.639 s)
REG-073 | Payments & wallet | IntegrityTests | Draw waits for checkouts in progress | Draw waits for checkouts in progress — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_draw_waits_for_checkouts_in_progress (0.554 s)
REG-074 | Responsible play | IntegrityTests | Forgot password is rate limited | Forgot password is rate limited — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::IntegrityTests::test_forgot_password_is_rate_limited (0.519 s)
REG-075 | Responsible play | IntegrityTests | Lowering a limit cancels a pending raise | Lowering a limit cancels a pending raise — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::IntegrityTests::test_lowering_a_limit_cancels_a_pending_raise (0.473 s)
REG-076 | Operations, integrity & recovery | IntegrityTests | Password change signs out other devices | Password change signs out other devices — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::IntegrityTests::test_password_change_signs_out_other_devices (0.911 s)
REG-077 | Payments & wallet | IntegrityTests | Paying for a cancelled competition is refunded | Paying for a cancelled competition is refunded — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_paying_for_a_cancelled_competition_is_refunded (0.499 s)
REG-078 | Payments & wallet | IntegrityTests | Payment provider down keeps basket | Payment provider down keeps basket — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_payment_provider_down_keeps_basket (0.522 s)
REG-079 | Competitions, draws & instant wins | IntegrityTests | Postal after closing is rejected | Postal after closing is rejected — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_postal_after_closing_is_rejected (0.463 s)
REG-080 | Competitions, draws & instant wins | IntegrityTests | Postal late wrong and limits | Postal late wrong and limits — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_postal_late_wrong_and_limits (0.688 s)
REG-081 | Competitions, draws & instant wins | IntegrityTests | Sell out does not bring draw forward | Sell out does not bring draw forward — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_sell_out_does_not_bring_draw_forward (0.572 s)
REG-082 | Payments & wallet | IntegrityTests | Staff cannot touch money | Staff cannot touch money — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::IntegrityTests::test_staff_cannot_touch_money (0.599 s)
REG-083 | Operations, integrity & recovery | IntegrityTests | Winner story needs permission | Winner story needs permission — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::IntegrityTests::test_winner_story_needs_permission (0.519 s)
REG-084 | Operations, integrity & recovery | IntegrityTests | Wrong amount is never fulfilled | Wrong amount is never fulfilled — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::IntegrityTests::test_wrong_amount_is_never_fulfilled (0.472 s)
REG-085 | General | PlatformTests | Closing freezes the entry list | Closing freezes the entry list — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::PlatformTests::test_closing_freezes_the_entry_list (0.611 s)
REG-086 | Payments & wallet | PlatformTests | Finance reconciles | Finance reconciles — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::PlatformTests::test_finance_reconciles (0.615 s)
REG-087 | Security & access | PlatformTests | Mfa required for admins | Mfa required for admins — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::PlatformTests::test_mfa_required_for_admins (0.763 s)
REG-088 | General | PlatformTests | Notifications are recorded once | Notifications are recorded once — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::PlatformTests::test_notifications_are_recorded_once (0.653 s)
REG-089 | Payments & wallet | PlatformTests | Payments paused and maintenance | Payments paused and maintenance — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::PlatformTests::test_payments_paused_and_maintenance (0.675 s)
REG-090 | Payments & wallet | PlatformTests | Provider failures pause payments | Provider failures pause payments — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::PlatformTests::test_provider_failures_pause_payments (0.536 s)
REG-091 | Competitions, draws & instant wins | PlatformTests | Redraw and prize claim | Redraw and prize claim — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::PlatformTests::test_redraw_and_prize_claim (0.825 s) | BUG-008 | Pass after fix
REG-092 | Security & access | PlatformTests | Roles limit what staff can do | Roles limit what staff can do — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::PlatformTests::test_roles_limit_what_staff_can_do (0.728 s)
REG-093 | General | PlatformTests | Sign out other devices | Sign out other devices — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::PlatformTests::test_sign_out_other_devices (0.694 s)
REG-094 | General | PlatformTests | Timeline flags cases health | Timeline flags cases health — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::PlatformTests::test_timeline_flags_cases_health (0.637 s)
REG-095 | Ticket allocation & basket | CustomerFeatureTests | Find my ticket and public list | Find my ticket and public list — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::CustomerFeatureTests::test_find_my_ticket_and_public_list (0.595 s)
REG-096 | Promotions, points & referrals | CustomerFeatureTests | Points history adds up | Points history adds up — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::CustomerFeatureTests::test_points_history_adds_up (0.612 s)
REG-097 | Promotions, points & referrals | CustomerFeatureTests | Referral rules | Referral rules — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::CustomerFeatureTests::test_referral_rules (0.823 s)
REG-098 | Customer & admin experience | CustomerFeatureTests | Results archive is permanent | Results archive is permanent — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CustomerFeatureTests::test_results_archive_is_permanent (0.585 s)
REG-099 | Customer & admin experience | CustomerFeatureTests | Search and watchlist | Search and watchlist — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CustomerFeatureTests::test_search_and_watchlist (0.645 s)
REG-100 | Operations, integrity & recovery | OpsTests | Backup is restore tested | Backup is restore tested — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OpsTests::test_backup_is_restore_tested (0.539 s)
REG-101 | General | OpsTests | Forty people racing for one number | Forty people racing for one number — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OpsTests::test_forty_people_racing_for_one_number (5.663 s)
REG-102 | General | OpsTests | Journey counts have no identifiers | Journey counts have no identifiers — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OpsTests::test_journey_counts_have_no_identifiers (0.714 s)
REG-103 | General | OpsTests | No question mechanic | No question mechanic — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OpsTests::test_no_question_mechanic (0.566 s)
REG-104 | Customer & admin experience | OpsTests | Staging never emails customers | Staging never emails customers — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::OpsTests::test_staging_never_emails_customers (0.476 s)
REG-105 | Ticket allocation & basket | OpsTests | Stampede never oversells | Stampede never oversells — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::OpsTests::test_stampede_never_oversells (4.740 s)
REG-106 | Customer & admin experience | CustomerExperienceTests | Account header and every tab reachable | Account header and every tab reachable — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CustomerExperienceTests::test_account_header_and_every_tab_reachable (0.634 s)
REG-107 | Customer & admin experience | CustomerExperienceTests | Dashboard shows what needs action | Dashboard shows what needs action — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CustomerExperienceTests::test_dashboard_shows_what_needs_action (0.620 s)
REG-108 | Ticket allocation & basket | CustomerExperienceTests | My tickets filters and ticket page | My tickets filters and ticket page — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::CustomerExperienceTests::test_my_tickets_filters_and_ticket_page (0.821 s)
REG-109 | Customer & admin experience | CustomerExperienceTests | Preferences record consent and unsubscribe | Preferences record consent and unsubscribe — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CustomerExperienceTests::test_preferences_record_consent_and_unsubscribe (0.601 s)
REG-110 | Customer & admin experience | CustomerExperienceTests | Support centre | Support centre — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CustomerExperienceTests::test_support_centre (0.910 s)
REG-111 | Customer & admin experience | CustomerExperienceTests | Transparency and states | Transparency and states — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CustomerExperienceTests::test_transparency_and_states (0.606 s)
REG-112 | Operations, integrity & recovery | OperationsTests | Anomaly alerts | Anomaly alerts — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_anomaly_alerts (0.490 s)
REG-113 | Operations, integrity & recovery | OperationsTests | Audit chain detects tampering | Audit chain detects tampering — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_audit_chain_detects_tampering (0.555 s)
REG-114 | Operations, integrity & recovery | OperationsTests | Audit viewer filters and export | Audit viewer filters and export — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_audit_viewer_filters_and_export (0.506 s)
REG-115 | Competitions, draws & instant wins | OperationsTests | Draw readiness blocks and logs once | Draw readiness blocks and logs once — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::OperationsTests::test_draw_readiness_blocks_and_logs_once (0.642 s)
REG-116 | Operations, integrity & recovery | OperationsTests | Feature flags | Feature flags — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_feature_flags (0.779 s)
REG-117 | Operations, integrity & recovery | OperationsTests | Integrity job reports problems | Integrity job reports problems — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_integrity_job_reports_problems (0.588 s)
REG-118 | Operations, integrity & recovery | OperationsTests | Ledgers are append only | Ledgers are append only — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_ledgers_are_append_only (0.460 s)
REG-119 | Operations, integrity & recovery | OperationsTests | Liability dashboard | Liability dashboard — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_liability_dashboard (0.569 s)
REG-120 | Operations, integrity & recovery | OperationsTests | Old audit rows are chained on upgrade | Old audit rows are chained on upgrade — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_old_audit_rows_are_chained_on_upgrade (0.437 s)
REG-121 | Operations, integrity & recovery | OperationsTests | Prelaunch validator blocks publish | Prelaunch validator blocks publish — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_prelaunch_validator_blocks_publish (0.533 s)
REG-122 | Operations, integrity & recovery | OperationsTests | Reconciliation finds mismatches | Reconciliation finds mismatches — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_reconciliation_finds_mismatches (0.518 s)
REG-123 | Operations, integrity & recovery | OperationsTests | Support case locks and history | Support case locks and history — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::OperationsTests::test_support_case_locks_and_history (0.621 s)
REG-124 | Operations, integrity & recovery | RecoveryTests | Disaster recovery drill | Disaster recovery drill — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::RecoveryTests::test_disaster_recovery_drill (0.841 s)
REG-125 | Customer & admin experience | ReportingTests | Business report figures and csv | Business report figures and csv — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::ReportingTests::test_business_report_figures_and_csv (0.576 s)
REG-126 | Customer & admin experience | ReportingTests | Errors are recorded and targets shown | Errors are recorded and targets shown — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::ReportingTests::test_errors_are_recorded_and_targets_shown (0.588 s)
REG-127 | Payments & wallet | SecurityTests | Concurrent withdrawals cannot overdraw | Concurrent withdrawals cannot overdraw — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_concurrent_withdrawals_cannot_overdraw (0.600 s)
REG-128 | Security & access | SecurityTests | Csrf required | Csrf required — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_csrf_required (0.599 s)
REG-129 | Security & access | SecurityTests | Idor other customers records | Idor other customers records — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_idor_other_customers_records (0.695 s)
REG-130 | Security & access | SecurityTests | Injection and escaping | Injection and escaping — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_injection_and_escaping (0.775 s)
REG-131 | Security & access | SecurityTests | Login lockout survives spoofed ip | Login lockout survives spoofed ip — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_login_lockout_survives_spoofed_ip (1.424 s)
REG-132 | Security & access | SecurityTests | Open redirects blocked | Open redirects blocked — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_open_redirects_blocked (1.306 s)
REG-133 | Security & access | SecurityTests | Price and quantity tampering | Price and quantity tampering — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_price_and_quantity_tampering (0.684 s)
REG-134 | Security & access | SecurityTests | Privilege escalation | Privilege escalation — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_privilege_escalation (0.615 s)
REG-135 | Security & access | SecurityTests | Promo cannot be reused or raced | Promo cannot be reused or raced — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_promo_cannot_be_reused_or_raced (0.628 s)
REG-136 | Security & access | SecurityTests | Security headers | Security headers — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_security_headers (0.664 s)
REG-137 | Security & access | SecurityTests | Webhook needs valid signature | Webhook needs valid signature — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::SecurityTests::test_webhook_needs_valid_signature (0.548 s)
REG-138 | Payments & wallet | MoneyJourneyTests | Cancellation refunds once even if repeated | Cancellation refunds once even if repeated — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MoneyJourneyTests::test_cancellation_refunds_once_even_if_repeated (0.534 s)
REG-139 | Payments & wallet | MoneyJourneyTests | Chargeback and dashboard refund flagged | Chargeback and dashboard refund flagged — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MoneyJourneyTests::test_chargeback_and_dashboard_refund_flagged (0.590 s)
REG-140 | Payments & wallet | MoneyJourneyTests | Failed and expired payments release everything | Failed and expired payments release everything — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MoneyJourneyTests::test_failed_and_expired_payments_release_everything (0.533 s)
REG-141 | Payments & wallet | MoneyJourneyTests | Full journey entry to withdrawal | Full journey entry to withdrawal — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MoneyJourneyTests::test_full_journey_entry_to_withdrawal (0.867 s)
REG-142 | Payments & wallet | MoneyJourneyTests | Interrupted session still gets tickets | Interrupted session still gets tickets — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MoneyJourneyTests::test_interrupted_session_still_gets_tickets (0.678 s)
REG-143 | Payments & wallet | MoneyJourneyTests | Reservation expiry without any webhook | Reservation expiry without any webhook — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MoneyJourneyTests::test_reservation_expiry_without_any_webhook (0.512 s)
REG-144 | Payments & wallet | MoneyJourneyTests | Wrong amount and cancelled competition | Wrong amount and cancelled competition — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MoneyJourneyTests::test_wrong_amount_and_cancelled_competition (0.550 s)
REG-145 | Payments & wallet | HardeningTests | Database error mid payment rolls back then retry succeeds | Database error mid payment rolls back then retry succeeds — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_database_error_mid_payment_rolls_back_then_retry_succeeds (0.501 s)
REG-146 | Security & access | HardeningTests | Database refuses impossible states | Database refuses impossible states — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_database_refuses_impossible_states (0.570 s)
REG-147 | Competitions, draws & instant wins | HardeningTests | Draw failing halfway leaves no trace and retries | Draw failing halfway leaves no trace and retries — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_draw_failing_halfway_leaves_no_trace_and_retries (0.655 s)
REG-148 | Security & access | HardeningTests | Email outage never blocks purchases | Email outage never blocks purchases — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_email_outage_never_blocks_purchases (0.574 s)
REG-149 | Security & access | HardeningTests | Jobs are idempotent even in parallel | Jobs are idempotent even in parallel — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_jobs_are_idempotent_even_in_parallel (0.638 s)
REG-150 | Payments & wallet | HardeningTests | Payment provider down at checkout | Payment provider down at checkout — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_payment_provider_down_at_checkout (0.511 s)
REG-151 | Payments & wallet | HardeningTests | Restart during checkout | Restart during checkout — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_restart_during_checkout (0.802 s)
REG-152 | Security & access | HardeningTests | Worker down jobs still run from web | Worker down jobs still run from web — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::HardeningTests::test_worker_down_jobs_still_run_from_web (0.522 s)
REG-153 | Security & access | AdminHardeningTests | Admin times out after inactivity | Admin times out after inactivity — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::AdminHardeningTests::test_admin_times_out_after_inactivity (0.704 s)
REG-154 | Security & access | AdminHardeningTests | Confirmation uses mfa when enabled | Confirmation uses mfa when enabled — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::AdminHardeningTests::test_confirmation_uses_mfa_when_enabled (0.517 s)
REG-155 | Security & access | AdminHardeningTests | Large adjustments need an administrator | Large adjustments need an administrator — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::AdminHardeningTests::test_large_adjustments_need_an_administrator (0.649 s) | BUG-004 | Pass after fix
REG-156 | Security & access | AdminHardeningTests | Sensitive actions need recent confirmation | Sensitive actions need recent confirmation — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::AdminHardeningTests::test_sensitive_actions_need_recent_confirmation (1.107 s)
REG-157 | Operations, integrity & recovery | MonitoringTests | Deep health and competition api | Deep health and competition api — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::MonitoringTests::test_deep_health_and_competition_api (0.486 s)
REG-158 | Operations, integrity & recovery | MonitoringTests | Error reports are scrubbed and have context | Error reports are scrubbed and have context — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::MonitoringTests::test_error_reports_are_scrubbed_and_have_context (0.432 s)
REG-159 | Payments & wallet | MonitoringTests | Payment drop and blocked draw alerts | Payment drop and blocked draw alerts — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::MonitoringTests::test_payment_drop_and_blocked_draw_alerts (0.487 s)
REG-160 | Operations, integrity & recovery | MonitoringTests | Release check | Release check — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::MonitoringTests::test_release_check (0.459 s)
REG-161 | Customer & admin experience | EvidenceTests | Cases need a reason and feed insights | Cases need a reason and feed insights — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::EvidenceTests::test_cases_need_a_reason_and_feed_insights (0.524 s)
REG-162 | Customer & admin experience | EvidenceTests | Select step counted anonymously | Select step counted anonymously — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::EvidenceTests::test_select_step_counted_anonymously (0.562 s)
REG-163 | Competitions, draws & instant wins | Phase6CustomerTests | Draw timeline buckets | Draw timeline buckets — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase6CustomerTests::test_draw_timeline_buckets (0.713 s)
REG-164 | Customer & admin experience | Phase6CustomerTests | Personal home and calendar | Personal home and calendar — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase6CustomerTests::test_personal_home_and_calendar (0.582 s)
REG-165 | Customer & admin experience | Phase6CustomerTests | Results show your entries and mine filter | Results show your entries and mine filter — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase6CustomerTests::test_results_show_your_entries_and_mine_filter (0.685 s)
REG-166 | Customer & admin experience | Phase6CustomerTests | Winner page choice delivery and progress | Winner page choice delivery and progress — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase6CustomerTests::test_winner_page_choice_delivery_and_progress (0.831 s)
REG-167 | Security & access | Phase6AdminTests | Control centre queues | Control centre queues — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase6AdminTests::test_control_centre_queues (0.621 s)
REG-168 | Security & access | Phase6AdminTests | Universal search | Universal search — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase6AdminTests::test_universal_search (0.560 s)
REG-169 | Customer & admin experience | Phase6OpsTests | Daily and weekly reports and releases | Daily and weekly reports and releases — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase6OpsTests::test_daily_and_weekly_reports_and_releases (0.517 s)
REG-170 | Security & access | Phase6OpsTests | Goodwill limits and roles | Goodwill limits and roles — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase6OpsTests::test_goodwill_limits_and_roles (0.511 s)
REG-171 | Promotions, points & referrals | Phase6OpsTests | Promo rules engine | Promo rules engine — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6OpsTests::test_promo_rules_engine (0.619 s)
REG-172 | Payments & wallet | Phase6OpsTests | Refund single order to wallet and card | Refund single order to wallet and card — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase6OpsTests::test_refund_single_order_to_wallet_and_card (0.721 s)
REG-173 | Customer & admin experience | Phase6OpsTests | Scheduled announcements | Scheduled announcements — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase6OpsTests::test_scheduled_announcements (0.552 s)
REG-174 | Promotions, points & referrals | Phase6GrowthTests | Content versions and competition terms | Content versions and competition terms — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6GrowthTests::test_content_versions_and_competition_terms (0.643 s)
REG-175 | Promotions, points & referrals | Phase6GrowthTests | Demo lifecycle command | Demo lifecycle command — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6GrowthTests::test_demo_lifecycle_command (1.094 s)
REG-176 | Promotions, points & referrals | Phase6GrowthTests | Diagnostics segments and experiments | Diagnostics segments and experiments — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6GrowthTests::test_diagnostics_segments_and_experiments (0.615 s)
REG-177 | Promotions, points & referrals | Phase6GrowthTests | Feedback and backlog | Feedback and backlog — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6GrowthTests::test_feedback_and_backlog (0.766 s)
REG-178 | Promotions, points & referrals | Phase6GrowthTests | Fuzzy search finds typos and winners | Fuzzy search finds typos and winners — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6GrowthTests::test_fuzzy_search_finds_typos_and_winners (0.491 s)
REG-179 | Promotions, points & referrals | Phase6GrowthTests | Points dashboard and milestones | Points dashboard and milestones — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6GrowthTests::test_points_dashboard_and_milestones (0.681 s)
REG-180 | Security & access | Phase6GrowthTests | Security log and csv downloads | Security log and csv downloads — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase6GrowthTests::test_security_log_and_csv_downloads (0.733 s)
REG-181 | Promotions, points & referrals | Phase6GrowthTests | Winner share card only with consent | Winner share card only with consent — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P1 | tests/test_app.py::Phase6GrowthTests::test_winner_share_card_only_with_consent (0.677 s)
REG-182 | General | MigrationTest | V1 database upgrades in place | V1 database upgrades in place — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::MigrationTest::test_v1_database_upgrades_in_place (0.291 s)
REG-183 | Customer & admin experience | Phase7TrustTests | Activity history and full data export | Activity history and full data export — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_activity_history_and_full_data_export (0.537 s)
REG-184 | Competitions, draws & instant wins | Phase7TrustTests | After draw check flags a broken result | After draw check flags a broken result — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase7TrustTests::test_after_draw_check_flags_a_broken_result (0.534 s)
REG-185 | Competitions, draws & instant wins | Phase7TrustTests | Draw record is checkable and free entries are equal | Draw record is checkable and free entries are equal — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase7TrustTests::test_draw_record_is_checkable_and_free_entries_are_equal (0.602 s)
REG-186 | Customer & admin experience | Phase7TrustTests | Emergency lock stops purchases and shows status | Emergency lock stops purchases and shows status — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_emergency_lock_stops_purchases_and_shows_status (0.736 s)
REG-187 | Customer & admin experience | Phase7TrustTests | Error reference shown and searchable | Error reference shown and searchable — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_error_reference_shown_and_searchable (0.496 s)
REG-188 | Customer & admin experience | Phase7TrustTests | Help centre search and status links | Help centre search and status links — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_help_centre_search_and_status_links (0.497 s)
REG-189 | Customer & admin experience | Phase7TrustTests | New device sign in and password reset notify | New device sign in and password reset notify — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_new_device_sign_in_and_password_reset_notify (0.590 s)
REG-190 | Customer & admin experience | Phase7TrustTests | New mechanic cannot publish without signoff | New mechanic cannot publish without signoff — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_new_mechanic_cannot_publish_without_signoff (0.470 s)
REG-191 | Competitions, draws & instant wins | Phase7TrustTests | Redraw needs a second admin when one exists | Redraw needs a second admin when one exists — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase7TrustTests::test_redraw_needs_a_second_admin_when_one_exists (0.703 s)
REG-192 | Customer & admin experience | Phase7TrustTests | Results centre filters and receipts | Results centre filters and receipts — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_results_centre_filters_and_receipts (0.598 s)
REG-193 | Customer & admin experience | Phase7TrustTests | Retention rules prune only what they say | Retention rules prune only what they say — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_retention_rules_prune_only_what_they_say (0.479 s)
REG-194 | Competitions, draws & instant wins | Phase7TrustTests | Selection ignores entry method | The pick only sees sorted ticket numbers: relabelling which tickets are postal never changes the winner. | As expected | Automated (Flask test client) | Pass | P0 | tests/test_app.py::Phase7TrustTests::test_selection_ignores_entry_method (0.489 s)
REG-195 | Customer & admin experience | Phase7TrustTests | Staff pages render | Staff pages render — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_staff_pages_render (0.694 s)
REG-196 | Customer & admin experience | Phase7TrustTests | Stage timeline on the competition page | Stage timeline on the competition page — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::Phase7TrustTests::test_stage_timeline_on_the_competition_page (0.646 s)
REG-197 | Customer & admin experience | CreateFormTests | Back button on every page with a sensible fallback | Back button on every page with a sensible fallback — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CreateFormTests::test_back_button_on_every_page_with_a_sensible_fallback (0.706 s)
REG-198 | Customer & admin experience | CreateFormTests | Create form shows only the chosen type | Create form shows only the chosen type — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CreateFormTests::test_create_form_shows_only_the_chosen_type (0.515 s)
REG-199 | Customer & admin experience | CreateFormTests | Prize rows on the create form | Prize rows on the create form — behaves as specified (assertions in the test) | As expected | Automated (Flask test client) | Pass | P2 | tests/test_app.py::CreateFormTests::test_prize_rows_on_the_create_form (0.540 s)
QA-CHK-03 | Checkout | Cancel | Cancel url releases reservation | Cancelling releases the reserved numbers for others; nothing is charged | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::CheckoutAudit::test_cancel_url_releases_reservation (0.450 s)
QA-CHK-02 | Checkout | Idempotency | Confirming payment twice gives one set of entries | Posting the payment confirmation repeatedly → one payment, one order, one set of tickets, one points award | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::CheckoutAudit::test_confirming_payment_twice_gives_one_set_of_entries (0.469 s)
QA-CHK-04 | Checkout | Out-of-order | Paying after cancel is never fulfilled as new tickets twice | Confirming a cancelled checkout never issues tickets that belong to someone else | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::CheckoutAudit::test_paying_after_cancel_is_never_fulfilled_as_new_tickets_twice (0.699 s)
QA-CHK-01 | Checkout | Success URL | Success url alone never creates a paid order | Visiting the confirmation URL without paying creates no paid order and no tickets | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::CheckoutAudit::test_success_url_alone_never_creates_a_paid_order (0.549 s)
QA-BSK-02 | Ticket allocation | Chosen numbers | Chosen numbers edge values | Out-of-range, zero, negative, duplicate and junk numbers never become tickets | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::BasketAudit::test_chosen_numbers_edge_values (0.563 s)
QA-BSK-05 | Basket | Closing | Competition closing while in basket | A competition that closes while in the basket can't be checked out | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::BasketAudit::test_competition_closing_while_in_basket (0.529 s)
QA-BSK-06 | Competition states | Entry | Draft closed and drawn competitions cannot be added | Draft, closed and drawn competitions refuse entries by direct POST | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::BasketAudit::test_draft_closed_and_drawn_competitions_cannot_be_added (0.511 s)
QA-BSK-04 | Basket | Price manipulation | Posted prices and totals are ignored | Extra price/total/discount fields in requests are ignored; server price charged | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::BasketAudit::test_posted_prices_and_totals_are_ignored (0.524 s)
QA-BSK-01 | Basket | Quantity | Quantity edge values rejected | 0, negative, decimal, non-numeric and huge quantities are refused server-side | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::BasketAudit::test_quantity_edge_values_rejected (0.596 s)
QA-BSK-03 | Ticket allocation | Sold numbers | Sold number cannot be bought again | A number someone else owns can't be bought; buyer isn't charged for it | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::BasketAudit::test_sold_number_cannot_be_bought_again (0.618 s)
QA-BSK-07 | Competition | Entry question | Wrong and missing answers | Wrong, missing or tampered answers never create entries | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::BasketAudit::test_wrong_and_missing_answers (0.540 s)
QA-DRW-03 | Draws | Failure injection | Failure after selection but before commit leaves nothing and retry gives same result | A crash during the draw leaves no partial result; the retry picks the same, single winner | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::DrawAudit::test_failure_after_selection_but_before_commit_leaves_nothing_and_retry_gives_same_result (0.547 s)
QA-DRW-04 | Draws | Notification failure | Failure while notifying keeps the draw and no second winner | If announcing fails after the draw, the result stands and retries don't redraw | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::DrawAudit::test_failure_while_notifying_keeps_the_draw_and_no_second_winner (0.660 s)
QA-DRW-01 | Draws | 1 entry | One entry draw | The only entry wins; one draw record; one prize claim | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::DrawAudit::test_one_entry_draw (0.581 s)
QA-DRW-05 | Draws | Refunded entries | Refunded entries are not in the draw | Tickets from a refunded order are excluded from the eligible pool | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::DrawAudit::test_refunded_entries_are_not_in_the_draw (0.680 s)
QA-DRW-02 | Draws | Duplicate execution | Running the draw again never makes another winner | Re-running the draw (job, manual button, direct call) never creates a second winner | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::DrawAudit::test_running_the_draw_again_never_makes_another_winner (0.590 s)
QA-IW-01 | Instant wins | Refresh/replay | Reveal is authoritative and repeatable | Revealing a play repeatedly returns the same result and pays once | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::InstantAudit::test_reveal_is_authoritative_and_repeatable (0.521 s)
QA-IW-02 | Instant wins | Unrevealed outcomes | Unrevealed prizes settle exactly once | The automatic settlement pays each unrevealed win once, even when run repeatedly | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::InstantAudit::test_unrevealed_prizes_settle_exactly_once (0.546 s)
QA-PTS-01 | DBX Points | Redemption | Points redemption edges | Can't redeem more than owned, zero, negative or junk; valid redemption adds site credit once | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::WalletAudit::test_points_redemption_edges (0.502 s)
QA-WD-03 | Withdrawals | Lifecycle | Rejected withdrawal returns money once | Requested → rejected returns the money exactly once; ledger reproduces the balance | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::WalletAudit::test_rejected_withdrawal_returns_money_once (0.522 s)
QA-WD-02 | Withdrawals | Balance types | Site credit and deposits cannot be withdrawn | Site credit and deposited funds can never be withdrawn as cash | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::WalletAudit::test_site_credit_and_deposits_cannot_be_withdrawn (0.454 s)
QA-WD-04 | Withdrawals | Verification | Unverified customer cannot withdraw | Unverified email blocks withdrawals | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::WalletAudit::test_unverified_customer_cannot_withdraw (0.447 s)
QA-WD-01 | Withdrawals | Amount edges | Withdrawal amount edges | Below £5, zero, negative, junk and over-balance refused; exactly £5 and the full balance allowed | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::WalletAudit::test_withdrawal_amount_edges (0.637 s)
QA-PRM-02 | Promotions | Basket change | Promo reevaluated when basket changes | A minimum-spend code applied then basket reduced is re-checked at payment | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::GrowthAudit::test_promo_reevaluated_when_basket_changes (0.486 s)
QA-PRM-01 | Promotions | Rules | Promo time window and limits | Expired and future codes refused; max uses and per-person limits enforced at payment | As expected | Automated (Flask test client) | Pass | P1 | tests/test_qa_audit.py::GrowthAudit::test_promo_time_window_and_limits (0.584 s)
QA-REF-01 | Referrals | Abuse | Self referral and invalid code | Invalid codes are ignored and nobody is rewarded for referring themselves | As expected | Automated (Flask test client) | Pass | P1 | tests/test_qa_audit.py::GrowthAudit::test_self_referral_and_invalid_code (0.526 s)
QA-RP-02 | Responsible play | Break | Break cannot be undone and blocks buying | A break blocks buying (direct POST too) and can't be shortened; logging in still works | As expected | Automated (Flask test client) | Pass | P1 | tests/test_qa_audit.py::SaferAudit::test_break_cannot_be_undone_and_blocks_buying (0.624 s) | BUG-001 | Pass after fix
QA-RP-01 | Responsible play | Limits | Limit raise waits and lower is instant | Lowering is immediate; raising waits 72 hours; spending over the limit is refused server-side | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::SaferAudit::test_limit_raise_waits_and_lower_is_instant (0.489 s)
QA-PST-02 | Free entry | Limits | Postal and paid entries share the per person limit | Free + paid entries by the same person can't exceed the per-person limit | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::PostalAudit::test_postal_and_paid_entries_share_the_per_person_limit (0.491 s)
QA-PST-01 | Free entry | Validation | Wrong answer and duplicate postal entries | A wrong-answer envelope is never entered; approving the same envelope twice gives one ticket | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::PostalAudit::test_wrong_answer_and_duplicate_postal_entries (0.500 s)
QA-JOB-01 | Background jobs | Repeat runs | All jobs twice back to back | Running every job twice in a row creates no duplicate money, tickets, draws or emails | As expected | Automated (Flask test client) | Pass | P1 | tests/test_qa_audit.py::AccountAudit::test_all_jobs_twice_back_to_back (0.511 s)
QA-REG-01 | Registration | Duplicates | Email case and duplicate signup | The same email in different case can't open a second account | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::AccountAudit::test_email_case_and_duplicate_signup (0.518 s)
QA-NOT-01 | Notifications | Isolation | Notifications belong to their owner | Customer A never sees or opens Customer B's notifications | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::AccountAudit::test_notifications_belong_to_their_owner (0.651 s)
QA-AUTH-01 | Password reset | Token reuse | Reset token single use and old password dead | A reset link works once; the old password stops working | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::AccountAudit::test_reset_token_single_use_and_old_password_dead (1.017 s)
QA-SRCH-01 | Search | Odd input | Search odd input | Special characters, very long and empty queries never error or reflect raw HTML | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::AccountAudit::test_search_odd_input (0.723 s)
QA-TIME-01 | Dates | British Summer Time | Uk clock changes | Closing times entered in UK time convert correctly across both clock changes | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::AccountAudit::test_uk_clock_changes (0.456 s)
QA-REG-02 | Registration | Input | Unicode and long names are handled | Unicode, emoji and very long names don't break signup or pages | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::AccountAudit::test_unicode_and_long_names_are_handled (0.680 s)
QA-MKT-01 | Marketing | Unsubscribe | Unsubscribe stops marketing not transactional | The one-click link turns marketing off; order confirmations still arrive | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::AccountAudit::test_unsubscribe_stops_marketing_not_transactional (0.503 s)
QA-UI-01 | Pages | Structure | Titles are plain text and ids unique | Every page title is plain text (no stray HTML) and no page repeats an element id | As expected | Automated (Flask test client) | Pass | P2 | tests/test_qa_audit.py::PageStructureAudit::test_titles_are_plain_text_and_ids_unique (1.013 s) | BUG-014 | Pass after fix
QA-RACE-02 | Approvals | Double approve | Approval carried out once even if approved twice | Approving the same request twice applies it once (one ledger line) | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::RaceRegressionAudit::test_approval_carried_out_once_even_if_approved_twice (0.643 s) | BUG-004 | Pass after fix
QA-RACE-04 | Wallet | Deposit refund | Deposit refund reserves before card refund | Refund is reserved before Stripe is called; a failed card refund returns the money | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::RaceRegressionAudit::test_deposit_refund_reserves_before_card_refund (0.453 s) | BUG-006 | Pass after fix
QA-RACE-01 | Draws | Double redraw | Double submitted redraw runs once | The same redraw form submitted repeatedly (or a stale form) redraws exactly once | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::RaceRegressionAudit::test_double_submitted_redraw_runs_once (0.587 s) | BUG-008 | Pass after fix
QA-RACE-03 | Admin money | Double submit | Wallet adjustment form double submit counts once | The same wallet-adjustment form submitted twice credits once | As expected | Automated (Flask test client) | Pass | P0 | tests/test_qa_audit.py::RaceRegressionAudit::test_wallet_adjustment_form_double_submit_counts_once (0.460 s) | BUG-009 | Pass after fix
SEC-ADM-02 | Security | Staff roles | Every admin route enforces its permission for every role | Each staff role can open only the admin pages its permissions allow; the rest are refused server-side | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::AdminPermissionSweep::test_every_admin_route_enforces_its_permission_for_every_role (1.727 s)
SEC-ADM-01 | Security | Admin access | Every admin route refuses customers and anonymous | Every admin URL (GET and POST) returns 404 to visitors and customers — never content or a 200 | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::AdminPermissionSweep::test_every_admin_route_refuses_customers_and_anonymous (1.490 s)
SEC-ADM-03 | Security | Hidden buttons | Money and draw posts refused for support role | Support staff can't trigger refunds, payouts, draws, redraws or wallet changes by direct POST | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::AdminPermissionSweep::test_money_and_draw_posts_refused_for_support_role (0.676 s)
SEC-CSRF-01 | Security | CSRF | Every post route needs the csrf token | Every POST endpoint (customer and admin) rejects a request without the anti-forgery token | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::CsrfAndMethodSweep::test_every_post_route_needs_the_csrf_token (1.178 s)
SEC-INP-02 | Security | Robustness | Query string junk on every page never 500 | Every GET page tolerates junk query parameters (huge, negative, script, SQL-like) without errors | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::CsrfAndMethodSweep::test_query_string_junk_on_every_page_never_500 (2.096 s)
SEC-INP-01 | Security | Robustness | Wrong methods and junk ids never 500 | Wrong HTTP methods give 405 and junk/huge/negative ids give 4xx — never a server error | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::CsrfAndMethodSweep::test_wrong_methods_and_junk_ids_never_500 (2.763 s)
SEC-SES-01 | Security | Session cookie | Cookie flags and private pages | Session cookie is HttpOnly + SameSite; account pages need login and are noindex/no-store | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::SessionAndHeaderSweep::test_cookie_flags_and_private_pages (0.865 s)
SEC-AUTH-01 | Security | Enumeration | Login and reset do not reveal accounts | Login and password reset give the same response for real and unknown emails | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::SessionAndHeaderSweep::test_login_and_reset_do_not_reveal_accounts (0.676 s)
SEC-HDR-01 | Security | Headers | Security headers on every html page | CSP, frame protection, nosniff and referrer policy are set on pages | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::SessionAndHeaderSweep::test_security_headers_on_every_html_page (0.779 s)
SEC-SEO-01 | SEO | Sitemap | Sitemap has no private urls | The sitemap lists public pages only — no account, admin, checkout or support URLs | As expected | Automated (Flask test client) | Pass | P0 | tests/test_security_audit.py::SessionAndHeaderSweep::test_sitemap_has_no_private_urls (0.512 s)
SCR-CRAWL | Navigation | Broken-link crawl | Crawl every reachable page as guest, customer, admin | No 404/500, titles/descriptions present | 433 pages, NO PROBLEMS FOUND | Flask test client | Pass | P1 | tests/qa_crawl.py
SCR-BROWSER | Pages | Console/network sweep | 436 pages × checks for console errors, failed requests, broken images, ids, names | No unexplained errors | 6,104 checks; real issues logged as BUG-010–014 and fixed; remainder test-environment artefacts (http://localhost SITE_URL) | Chromium (Playwright) | Pass | P2 | tests/browser_audit.py; scratchpad browser_audit.json | BUG-010..014 | Pass after fix
SCR-RESP | Mobile | Responsive widths | 13 widths 320–1920 + iPhone 13/Pixel 7/iPad Mini emulation | No sideways scrolling | Clean after fixes (re-swept 320–414px) | Chromium (Playwright) device emulation | Pass | P2 | tests/browser_audit.py + ovf sweep | BUG-012,013 | Pass after fix
SCR-JOURNEY | Checkout | Mobile purchase journey | iPhone 13: log in → competition → answer → add → basket → pay → confirmation → My tickets | Every step works; tap targets ≥24px | All 8 steps passed; no small tap targets | Chromium (Playwright) iPhone 13 emulation | Pass | P1 | journey_*.png screenshots
SCR-STORAGE | Privacy | Cookie/storage audit | Inventory cookies, storage, third-party requests vs cookie policy | Live behaviour matches the policy | 1 cookie (session: HttpOnly, SameSite=Lax), sessionStorage dbxPrev, service worker, no third parties; policy updated | Chromium (Playwright) | Pass | P2 | browser_audit.json storage | BUG-011 | Pass after fix
SCR-PERF | Performance | Page weight budgets | Homepage, listing, competition, games, account, basket, results | Within budget | ALL WITHIN BUDGET; CSS 13.4K gz | Chromium (Playwright) | Pass | P2 | tests/perf_budget.py
SCR-A11Y | Accessibility | Keyboard walkthrough + axe | Tab through key journeys; automated axe scan | Focus visible, reachable, no axe violations | NO PROBLEMS FOUND | Chromium (Playwright) | Pass | P2 | tests/a11y_keyboard.py
SCR-STRESS | Ticket allocation | Process-level concurrency | 24 buyers in 24 OS processes race for the last tickets | Never oversold, no duplicate numbers | PASS | Chromium (Playwright) | Pass | P0 | tests/stress_concurrency.py
RACE-S1[N=1] | Race conditions | Last 1 ticket, 20+ buyers | Last 1 ticket, 20+ buyers: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S1[N=2] | Race conditions | Last 2 tickets | Last 2 tickets: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S1[N=5] | Race conditions | Last 5 tickets | Last 5 tickets: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S1[N=10] | Race conditions | Last 10 tickets | Last 10 tickets: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S2 | Race conditions | Same wallet, two tabs | Same wallet, two tabs: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S3a | Race conditions | Concurrent withdrawals | Concurrent withdrawals: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S3b | Race conditions | Withdrawal + purchase at once | Withdrawal + purchase at once: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S4 | Race conditions | Concurrent points redemption | Concurrent points redemption: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S5a | Race conditions | Single-use promo, many users | Single-use promo, many users: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S5b | Race conditions | Per-user promo, same user twice | Per-user promo, same user twice: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S6a | Race conditions | Duplicate demo-pay confirmations | Duplicate demo-pay confirmations: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S6b | Race conditions | Concurrent identical webhooks | Concurrent identical webhooks: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S6c | Race conditions | Credit-card payment, duplicate webhooks | Credit-card payment, duplicate webhooks: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | FAILED before fix → PASS after fix | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log | BUG-007 | Pass after fix
RACE-S7a | Race conditions | Concurrent draw execution | Concurrent draw execution: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S7b | Race conditions | Redraw double-submitted ×6 | Redraw double-submitted ×6: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | FAILED before fix → PASS after fix — Rounds 2–3 queued for two-person approval (correct) | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log | BUG-008 | Pass after fix
RACE-S8 | Race conditions | Free daily play claimed concurrently | Free daily play claimed concurrently: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S9a | Race conditions | Same play revealed concurrently | Same play revealed concurrently: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S9b | Race conditions | Settlement racing a reveal | Settlement racing a reveal: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S10 | Race conditions | Referral reward twice | Referral reward twice: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
RACE-S11 | Race conditions | Approval approved concurrently | Approval approved concurrently: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | FAILED before fix → PASS after fix — Round 1: no second admin so applied directly (correct) | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log | BUG-004 | Pass after fix
RACE-S12a | Race conditions | Deposit refund clicked ×6 | Deposit refund clicked ×6: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | FAILED before fix → PASS after fix | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log | BUG-005 | Pass after fix
RACE-S12b | Race conditions | Deposit refund racing a purchase | Deposit refund racing a purchase: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | FAILED before fix → PASS after fix | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log | BUG-006 | Pass after fix
RACE-S13 | Race conditions | Goodwill credit concurrently | Goodwill credit concurrently: simultaneous real HTTP requests from separate processes, 3 rounds | Exactly one valid outcome; balances never negative; no duplicates | PASS 3/3 | Real server, multi-process | Pass | P0 | tests/race_audit.py; scratchpad race3.log
LOAD-50 | Load | Non-stop browsing + checkout race | 50 non-stop users for 30 s (gunicorn 3×4, 4 cores) | 0 errors; p95 < 2 s; contested ticket sold once | 365 req/s, p95 29 ms, 0 errors | gunicorn (production config) | Pass | P1 | tests/load_test.py
LOAD-150 | Load | Non-stop browsing + checkout race | 150 non-stop users for 30 s (gunicorn 3×4, 4 cores) | 0 errors; p95 < 2 s; contested ticket sold once | 573 req/s, p95 294 ms, 0 errors | gunicorn (production config) | Pass | P1 | tests/load_test.py
LOAD-300 | Load | Non-stop browsing + checkout race | 300 non-stop users for 30 s (gunicorn 3×4, 4 cores) | 0 errors; p95 < 2 s; contested ticket sold once | 565 req/s, p95 946 ms, 0 errors | gunicorn (production config) | Pass | P1 | tests/load_test.py
DR-01 | Recovery | Backup → restore → verify | Take a backup of seeded data, restore to an isolated copy, verify pages, data, draws | Drill PASSED with real data | PASSED: 2 users, 5 comps, 55 tickets, 1 draw recomputes; RTO 0.4 s, RPO 0 h | CLI | Pass | P0 | flask dr-drill
STATIC-01 | Code | Static analysis | pyflakes over app/ and tests | No undefined names | None; dead code removed | pyflakes | Pass | P3 | pyflakes | BUG-002,003 | Pass after fix
STATIC-02 | Security | Secret scan | Search code + full git history for live keys/private keys/.env | None | Only a fake key inside the error-scrubbing test | git grep | Pass | P0 | git history scan
STATIC-03 | Pages | Template compile | Compile all 111 Jinja templates | 0 errors | 0 errors | Jinja | Pass | P1 | template compile
NR-01 | Not run here | Safari, Firefox, Edge | Safari, Firefox, Edge | — | Only Chromium is installed in the test environment — needs a person with those browsers | — | Not run | — | docs/qa/QA-REPORT.md
NR-02 | Not run here | Physical iPhone / Android / tablet | Physical iPhone / Android / tablet | — | No physical devices here; Chromium device emulation used instead | — | Not run | — | docs/qa/QA-REPORT.md
NR-03 | Not run here | Email rendering in Gmail/Outlook/Apple Mail | Email rendering in Gmail/Outlook/Apple Mail | — | Needs real mailboxes; HTML verified to use absolute links and the branded template | — | Not run | — | docs/qa/QA-REPORT.md
NR-04 | Not run here | Real Stripe test-mode end-to-end | Real Stripe test-mode end-to-end | — | Stripe is simulated in tests; run a test-mode purchase/refund on staging | — | Not run | — | docs/qa/QA-REPORT.md
NR-05 | Not run here | Production smoke test | Production smoke test | — | Needs the live server after deployment (owner) | — | Not run | — | docs/qa/QA-REPORT.md
NR-06 | Not run here | Independent penetration test | Independent penetration test | — | Needs an external tester under docs/PENTEST-SCOPE.md | — | Not run | — | docs/qa/QA-REPORT.md
NR-07 | Not run here | Dependency vulnerability scan (pip-audit) | Dependency vulnerability scan (pip-audit) | — | Declined at the permission prompt; 4 pinned dependencies (Flask, gunicorn, requests, Pillow) | — | Not run | — | docs/qa/QA-REPORT.md
NR-08 | Not run here | Exploratory testing by fresh testers | Exploratory testing by fresh testers | — | Needs people who didn't build the site | — | Not run | — | docs/qa/QA-REPORT.md
NR-09 | Not run here | Legal sign-off of terms and mechanics | Legal sign-off of terms and mechanics | — | Needs a solicitor | — | Not run | — | docs/qa/QA-REPORT.md

## Bugs
id | severity | area | title | found_by | reproduce | fix | status | retest | tests
BUG-001 | P1 | Responsible play | A responsible-play break could be shortened by choosing a shorter break | tests/test_qa_audit.py SaferAudit (QA-RP-02) | Account → Responsible play → take a 7-day break, then submit the form again with 1 day: excluded_until moved from +7 days to +1 day. | start_break() only ever extends the break (keeps the later end date); message now states the end date and that breaks can't be shortened. | Fixed | QA-RP-02 passes; full suite 237/237 | test_break_cannot_be_undone_and_blocks_buying
BUG-002 | P3 | SEO | Sitemap code contradicted its description (180-day cut-off computed but never used) | Static analysis (pyflakes) | app/routes.py sitemap(): unused 'cutoff'; docstring said results drop out after 180 days. | Behaviour kept (results are a permanent archive); dead code removed and description corrected. | Fixed | test_sitemap_keeps_recent_results_and_drops_cancelled passes | test_sitemap_keeps_recent_results_and_drops_cancelled
BUG-003 | P3 | Code quality | Unused variables/imports left in routes, control, checks | Static analysis (pyflakes) | pyflakes app/ | Removed the unused variables that could hide logic slips; no undefined names exist. | Fixed | pyflakes: no undefined names; suite passes
BUG-004 | P0 | Admin money / approvals | One approved large wallet adjustment could be applied several times when approved at the same moment | tests/race_audit.py S11 (8 simultaneous approvals → customer credited 3×) | Two admins (or a double-click) press Approve on the same request at once. | decide() now checks, carries out and records the approval in one locked database transaction; executors run inside it. | Fixed | S11 PASS (1 ledger line); QA-RACE-02 passes | test_approval_carried_out_once_even_if_approved_twice, test_large_adjustments_need_an_administrator
BUG-005 | P0 | Wallet / deposits | Refunding unspent deposits sent the card refund to Stripe once per click (6 clicks → 6 refunds of £20) | tests/race_audit.py S12a | Press 'Refund unspent deposits' repeatedly / in two tabs at once. | Refund reserved in the wallet ledger inside a locked transaction before Stripe is called; Stripe Idempotency-Key on every refund; failed card refund puts the money back. | Fixed | S12a PASS 3/3; QA-RACE-04 passes | test_deposit_refund_reserves_before_card_refund
BUG-006 | P0 | Wallet / deposits | A deposit refund racing a purchase could refund money that had just been spent on entries | tests/race_audit.py S12b (£10 deposit: £22 refunded + £10 spent) | Refund unspent deposits while a checkout paid from the same deposit runs. | Same reservation-first design as BUG-005: the refund amount is worked out and taken from the wallet in the same locked transaction. | Fixed | S12b PASS 3/3 | test_deposit_refund_reserves_before_card_refund
BUG-007 | P0 | Payments / webhooks | Duplicate Stripe webhooks for a credit-card payment sent the automatic refund up to 10 times | tests/race_audit.py S6c | Stripe delivers the same checkout.session.completed event several times at once for a credit-card payment. | Refusal claims a one-time key (once_keys table) before refunding; Stripe Idempotency-Key per checkout/deposit. | Fixed | S6c PASS 3/3; credit-card tests pass | test_credit_card_refunded_tickets_released_balance_returned
BUG-008 | P0 | Draws | A double-submitted redraw ran several redraws (6 submissions → 5 redraws, winner changed 5 times) | tests/race_audit.py S7b | Press Redraw several times quickly or submit the same form twice. | Redraw form carries the id of the result it replaces (now required); the redraw runs only if that is still the current result, inside one transaction. | Fixed | S7b round 1 PASS (1 redraw); QA-RACE-01 passes | test_double_submitted_redraw_runs_once, test_redraw_and_prize_claim
BUG-009 | P1 | Admin money | Wallet adjustment / goodwill forms could be applied twice by a double-click or refresh | Code review during the race audit | Double-click 'Adjust' on a customer's admin page. | One-time form token checked server-side; a repeat shows 'already done'. | Fixed | QA-RACE-03 passes | test_wallet_adjustment_form_double_submit_counts_once
BUG-010 | P2 | Admin UI | Reports and Compliance pages had a page section pasted into the <title> and <head> (garbled tab title, duplicate ids) | tests/browser_audit.py (duplicate_id) | Open Admin → Reports or Compliance; look at the tab title / page source. | Stray copies removed; regression test checks every page title is plain text and ids are unique. | Fixed | QA-UI-01 passes | test_titles_are_plain_text_and_ids_unique
BUG-011 | P2 | Legal / cookies | Cookie policy didn't mention the session-storage item used by the Back button | tests/browser_audit.py storage inventory | Compare browser storage (sessionStorage dbxPrev) with /cookies. | Cookie policy now describes it. | Fixed | QA-UI-01 passes | test_titles_are_plain_text_and_ids_unique
BUG-012 | P2 | Mobile | Wallet page scrolled sideways on 320px-wide phones | tests/browser_audit.py responsive | Open My account → Wallet at 320px width. | Balance cards can shrink; smaller padding/fonts under 360px. | Fixed | Overflow sweep 320–414px clean
BUG-013 | P3 | Mobile (admin) | Admin competition page and Reports scrolled sideways on phones | tests/browser_audit.py responsive | Open an admin competition or Reports at 320–414px. | Prize table and report panels scroll inside their box; admin dropdowns fit the screen. | Fixed | Overflow sweep clean
BUG-014 | P3 | Assets | /favicon.ico returned 404 (browsers request it automatically) | tests/browser_audit.py console errors | Request /favicon.ico | Redirects to the site icon. | Fixed | QA-UI-01 passes | test_titles_are_plain_text_and_ids_unique